## TEAM17 Plan
OSS Final Project - TEAM 17
2018년 11월 24일 기준
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 (11/1 ~ 11/7) | [6 empty] | WEEK 2 (11/8 ~ 11/14) | [6 empty] | WEEK 3 (11/15 ~ 11/21) | [6 empty] | WEEK 4 (11/22 ~ 11/28) | [6 empty] | WEEK 5 (11/29 ~ 12/5)
[7 empty] | Thur | Fri | Sat | Sun | Mon | Tues | Wed | Thur | Fri | Sat | Sun | Mon | Tues | Wed | Thur | Fri | Sat | Sun | Mon | Tues | Wed | Thur | Fri | Sat | Sun | Mon | Tues | Wed | Thur | Fri | Sat | Sun | Mon | Tues | Wed
Final Project 시작을 위한 준비 과정
| 팀프로젝트를 위한 팀 구성 | 2018-11-01 | 2018-11-13 | 9 | 모두 | 100% | bar: WEEK 1 (11/1 ~ 11/7) Thur to WEEK 2 (11/8 ~ 11/14) Tues; WEEK 4 (11/22 ~ 11/28) Thur to WEEK 4 (11/22 ~ 11/28) Sat
| OSS Mission3 끝내기 | 2018-10-28 | 2018-11-06 | 7 | 각자 | 100% | bar: WEEK 1 (11/1 ~ 11/7) Thur to WEEK 1 (11/1 ~ 11/7) Tues; WEEK 4 (11/22 ~ 11/28) Thur to WEEK 4 (11/22 ~ 11/28) Sat
| OSS TeamMission1 끝내기 | 2018-11-06 | 2018-11-20 | 11 | 모두 | 100% | bar: WEEK 1 (11/1 ~ 11/7) Wed to WEEK 3 (11/15 ~ 11/21) Thur; WEEK 3 (11/15 ~ 11/21) Sat to WEEK 3 (11/15 ~ 11/21) Mon; WEEK 4 (11/22 ~ 11/28) Thur to WEEK 4 (11/22 ~ 11/28) Sat
| OSS Mission5 끝내기 | 2018-11-14 | 2018-11-22 | 7 | 각자 | 100% | bar: WEEK 2 (11/8 ~ 11/14) Thur to WEEK 4 (11/22 ~ 11/28) Sat
| OSS Mission6 끝내기 | 2018-11-22 | 2018-11-30 | 7 | 각자 | 33% | bar: WEEK 4 (11/22 ~ 11/28) Thur to WEEK 5 (11/29 ~ 12/5) Fri
| OSS Mission7 끝내기 |  |  | 0 | 각자 | 0% | bar: WEEK 4 (11/22 ~ 11/28) Thur to WEEK 4 (11/22 ~ 11/28) Sat
주제 선정 및 계획 수립
| 오픈소스 탐색 + 주제 아이디어 도출 | 2018-11-18 | 2018-11-20 | 2 | 각자 | 100% | bar: WEEK 3 (11/15 ~ 11/21) Sun to WEEK 3 (11/15 ~ 11/21) Tues; WEEK 4 (11/22 ~ 11/28) Thur to WEEK 4 (11/22 ~ 11/28) Sat
| 아이디어 토론 및 주제 선정 | 2018-11-20 | 2018-11-20 | 1 | 모두 | 100% | bar: WEEK 3 (11/15 ~ 11/21) Tues; WEEK 4 (11/22 ~ 11/28) Thur to WEEK 4 (11/22 ~ 11/28) Sat
| 주제 선정 이유 | 2018-11-20 | 2018-11-24 | 4 | 모두 | 10% | bar: WEEK 3 (11/15 ~ 11/21) Tues to WEEK 4 (11/22 ~ 11/28) Sun
| Git 및 GitHub 스터디 | 2018-11-14 | 2018-11-22 | 7 | 모두 | 100% | bar: WEEK 2 (11/8 ~ 11/14) Wed to WEEK 4 (11/22 ~ 11/28) Sat
| Pivotal Tracker 활용 방법 정리 | 2018-11-21 | 2018-11-24 | 3 | 최민지 | 40% | bar: WEEK 3 (11/15 ~ 11/21) Wed to WEEK 4 (11/22 ~ 11/28) Sat
| Long-term 계획 수립 | 2018-11-21 | 2018-11-26 | 4 | 최민지 | 80% | bar: WEEK 3 (11/15 ~ 11/21) Wed to WEEK 4 (11/22 ~ 11/28) Mon
오픈소스 분석
| HotCRP 기능 분석 (웹사이트) | 2018-11-22 | 2018-11-23 | 2 | 각자 | 80% | bar: WEEK 4 (11/22 ~ 11/28) Thur to WEEK 4 (11/22 ~ 11/28) Sat
| HotCRP 기능 summarization | 2018-11-24 |  |  | ? | 20% | bar: WEEK 4 (11/22 ~ 11/28) Thur to WEEK 4 (11/22 ~ 11/28) Sat
| 논문 관리 시스템 시각화 |  |  |  | ? | 40% | bar: WEEK 4 (11/22 ~ 11/28) Thur to WEEK 4 (11/22 ~ 11/28) Sat
| 오픈소스 주요 코드 분석 |  |  |  | 각자 | 0% | bar: WEEK 4 (11/22 ~ 11/28) Thur to WEEK 4 (11/22 ~ 11/28) Sat
| 분석 결과 토론 |  |  |  | 모두 | 0% | bar: WEEK 4 (11/22 ~ 11/28) Thur to WEEK 4 (11/22 ~ 11/28) Sat
| 오픈소스 코드 분석 마무리 |  |  |  | ? | 0% | bar: WEEK 4 (11/22 ~ 11/28) Thur to WEEK 4 (11/22 ~ 11/28) Sat
Enhancement Proposal & Discussion
| 추가하고 싶은 기능 아이디어 제시 | 2018-11-22 | 2018-11-24 | 2 | 각자 | 100% | bar: WEEK 4 (11/22 ~ 11/28) Thur to WEEK 4 (11/22 ~ 11/28) Sat
| New Feature Proposal 아이디어 최종 | 2018-11-24 | 2018-11-24 | 0 | 모두 | 100% | bar: WEEK 4 (11/22 ~ 11/28) Thur to WEEK 4 (11/22 ~ 11/28) Sat
0% | bar: WEEK 4 (11/22 ~ 11/28) Thur to WEEK 4 (11/22 ~ 11/28) Sat
0% | bar: WEEK 4 (11/22 ~ 11/28) Thur to WEEK 4 (11/22 ~ 11/28) Sat
Being Contributor
0% | bar: WEEK 4 (11/22 ~ 11/28) Thur to WEEK 4 (11/22 ~ 11/28) Sat
0% | bar: WEEK 4 (11/22 ~ 11/28) Thur to WEEK 4 (11/22 ~ 11/28) Sat
0% | bar: WEEK 4 (11/22 ~ 11/28) Thur to WEEK 4 (11/22 ~ 11/28) Sat
0% | bar: WEEK 4 (11/22 ~ 11/28) Thur to WEEK 4 (11/22 ~ 11/28) Sat
정리 및 브리핑 준비
0% | bar: WEEK 4 (11/22 ~ 11/28) Thur to WEEK 4 (11/22 ~ 11/28) Sat
0% | bar: WEEK 4 (11/22 ~ 11/28) Thur to WEEK 4 (11/22 ~ 11/28) Sat
0% | bar: WEEK 4 (11/22 ~ 11/28) Thur to WEEK 4 (11/22 ~ 11/28) Sat
0% | bar: WEEK 4 (11/22 ~ 11/28) Thur to WEEK 4 (11/22 ~ 11/28) Sat
Formulas:
DURATION (WORK DAYS) = NETWORKDAYS([START DATE],[END DATE])